## Gantt
Gantt CHART
Year/Period | 1 | [7 empty] | 2 | [6 empty] | 3
Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
PHASE I. PROTOCOL HARMONISATION
Delphi interview
first round of experts’ comments
development of second questionnaire
second round of experts’ comments
teleconference | [5 empty] | s(
finalization of harmonized protocol
PHASE II. APPLICATION OF HARMON. PROTOCOL
Environment for hippo tracing & qualification
environment development
tracings of benchmark images
Testing error variance of harmonized protocol
Testing variance due to atrophy and atrophy rates
Validation with histopathol. conf'd specimens
PHASE III. DEVELOPMENT OF HIPPOCAMPAL PROBABILISTIC MASKS
Development of masks
PHASE IV. DELIVERABLE PRODUCTION
Draft report
Teleconference | [20 empty] | s(
Final report
End of project

## Budget
| EUROS |  |  |  | US DOLLARS
| Period 1 | Period 2 | Period 3 | Total | Period 1 | Period 2 | Period 3 | Total
Proposed Start Date (mm/dd/yyyy) | 2010-09-01 | 2011-05-02 | 2011-12-01 |  | 2010-09-01 | 2011-05-02 | 2011-12-01
Proposed End Date (mm/dd/yyyy) | 2011-05-01 | 2011-11-30 | 2012-08-31 |  | 2011-05-01 | 2011-11-30 | 2012-08-31
Enter Personnel Costs:
Salaries & Wages | 45200 | 66093 | 31750 | 143043 | 57449.2 | 84004.203 | 40354.25 | 181807.653
Fringe Benefits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SubTotal: Personnel Costs | 45200 | 66093 | 31750 | 143043 | 57449.2 | 84004.203 | 40354.25 | 181807.653
Enter Non-personnel Costs:
Laboratory Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Laboratory Supplies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Animal Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total: Non-Personnel costs: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enter F&A (indirect) costs:
Facilities & Admin Costs | 4520 | 6609.3 | 3175 | 14304.3 | 5744.92 | 8400.4203 | 4035.425 | 18180.7653
Sub Total: Indirect costs: | 4520 | 6609.3 | 3175 | 14304.3 | 5744.92 | 8400.4203 | 4035.425 | 18180.7653
Total Costs: | 49720 | 72702.3 | 34925 | 157347.3 | 63194.12 | 92404.6233 | 44389.675 | 199988.4183
Indicate any other funding in support of this project
Applicant Cost Share | 30000 | 30000 | 41000 | 101000 | 38130 | 38130 | 52111 | 128371
Other Cost Share | 25000 | 15350 | 25000 | 65350 | 31775 | 19509.85 | 31775 | 83059.85